## BLANK Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING |  |  |  |  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Proof of Concept |  | 12 | 12 | 0 | 2021-12-26 | 2022-01-08 | 14 | 100%
1.1 | Project Specification | Alessandro / Stefano / Davide | 2 | 2 | 0 |  |  |  | 100%
1.2 | Define Scenarios / User Stories | Alessandro / Stefano / Davide | 2 | 2 | 0 |  |  |  | 100%
1.3 | Mockups | Davide | 2 | 2 | 0 |  |  |  | 100%
1.4 | Function points | Stefano | 2 | 2 | 0 |  |  |  | 100%
1.5 | Software architecture | Alessandro / Stefano / Davide | 2 | 2 | 0 |  |  |  | 100%
1.6 | COCOMO II | Stefano | 2 | 2 | 0 |  |  |  | 100%
2 | Sprint 1 |  | 21 | 21 | 0 | 2022-02-19 | 2022-03-05 | 15 | 100%
2.1 | Account registration | Davide | 2 | 2 | 0 |  |  |  | 100%
2.2 | Login | Davide | 2 | 2 | 0 |  |  |  | 100%
2.3 | Add a Travel | Stefano | 1 | 1 | 0 |  |  |  | 100%
2.4 | Add Expense | Alessandro | 1 | 1 | 0 |  |  |  | 100%
2.5 | Remove Expense | Alessandro | 2 | 2 | 0 |  |  |  | 100%
2.6 | Remove a travel | Stefano | 2 | 2 | 0 |  |  |  | 100%
2.7 | Logout | Davide | 2 | 2 | 0 |  |  |  | 100%
2.8 | Delete account | Davide | 2 | 2 | 0 |  |  |  | 100%
2.9 | View user information | Stefano | 2 | 2 | 0 |  |  |  | 100%
2.10 | Get all travels | Stefano | 1 | 1 | 0 |  |  |  | 100%
2.11 | End travel | Alessandro | 1 | 1 | 0 |  |  |  | 100%
2.12 | Daily budget | Alessandro | 1 | 1 | 0 |  |  |  | 100%
2.13 | View travel | Alessandro | 1 | 1 | 0 |  |  |  | 100%
2.14 | View Day of the travel | Alessandro | 1 | 1 | 0 |  |  |  | 100%
3 | Sprint 2 |  | 27 | 27 | 0 | 2022-03-07 | 2022-03-21 | 15 | 100%
3.1 | Account registration | Davide | 2 | 2 | 0 |  |  |  | 100%
3.2 | Login | Davide | 2 | 2 | 0 |  |  |  | 100%
3.3 | View user information | Stefano | 2 | 2 | 0 |  |  |  | 100%
3.4 | Add a travel | Stefano | 1 | 1 | 0 |  |  |  | 100%
3.5 | Add Expense | Alessandro | 1 | 1 | 0 |  |  |  | 100%
3.6 | Remove Travel | Stefano | 2 | 2 | 0 |  |  |  | 100%
3.7 | Remove Expense | Alessandro | 2 | 2 | 0 |  |  |  | 100%
3.8 | Get all travels | Stefano | 1 | 1 | 0 |  |  |  | 100%
3.9 | End travel | Stefano | 1 | 1 | 0 |  |  |  | 100%
3.10 | Daily budget | Alessandro | 1 | 1 | 0 |  |  |  | 100%
3.11 | View travel | Alessandro | 1 | 1 | 0 |  |  |  | 100%
3.12 | View Day of the travel | Alessandro | 1 | 1 | 0 |  |  |  | 100%
3.13 | Delete account | Davide | 2 | 2 | 0 |  |  |  | 100%
3.14 | Logger | Stefano-Davide-Alessandro | 8 | 8 | 0 |  |  |  | 100%
4 | Sprint 3 |  | 16 | 16 | 0 | 2022-03-22 | 2022-04-01 | 11 | 100%
4.1 | Travel comparison | Stefano | 4 | 4 | 0 |  |  |  | 100%
4.2 | Expenses comparison by categories | Alessandro | 4 | 4 | 0 |  |  |  | 100%
4.3 | Expenses comparison by days | Alessandro | 4 | 4 | 0 |  |  |  | 100%
4.4 | Style | Davide | 4 | 4 | 0 |  |  |  | 100%
4 | Final |  | 8 | 8 | 0 | 2022-04-02 | 2022-04-06 | 5 | 100%
4.1 | Presentation | Alessandro / Stefano / Davide | 2 | 2 | 0 |  |  |  | 100%
4.2 | Testing | Alessandro / Stefano / Davide | 4 | 4 | 0 |  |  |  | 100%
4.3 | Documentation | Alessandro / Stefano / Davide | 2 | 2 | 0 |  |  |  | 100%
|  |  | ESTIMATE | COMPLETED | REMAINING | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 84 | 84 | 0 | 1.4 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL HOURS
[9 empty] | PLAN | 84 | 82.6 | 81.2 | 79.8 | 78.4 | 77 | 75.6 | 74.2 | 72.8 | 71.4 | 70 | 68.6 | 67.2 | 65.8 | 64.4 | 63 | 61.6 | 60.2 | 58.8 | 57.4 | 56 | 54.6 | 53.2 | 51.8 | 50.4 | 49 | 47.6 | 46.2 | 44.8 | 43.4 | 42 | 40.6 | 39.2 | 37.8 | 36.4 | 35 | 33.6 | 32.2 | 30.8 | 29.4 | 28 | 26.6 | 25.2 | 23.8 | 22.4 | 21 | 19.6 | 18.2 | 16.8 | 15.4 | 14 | 12.6 | 11.2 | 9.8 | 8.4 | 7 | 5.6 | 4.2 | 2.8 | 1.4
[9 empty] | ESTIMATE | 84 | 83 | 82 | 81 | 80 | 79 | 79 | 79 | 79 | 78 | 77 | 75 | 74 | 72 | 72 | 69 | 69 | 67 | 66 | 64 | 63 | 61 | 60 | 60 | 58 | 56 | 55 | 53 | 52 | 51 | 50 | 49 | 48 | 46 | 45 | 43 | 43 | 41 | 39 | 36 | 33 | 30 | 27 | 27 | 24 | 22 | 20 | 19 | 17 | 15 | 15 | 14 | 12 | 10 | 8 | 6 | 6 | 5 | 3 | 2 | 2833
[8 empty] | Enter hours completed per day ----> | HRS COMPLETED | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 2 | 0 | 3 | 0 | 2 | 1 | 2 | 1 | 2 | 1 | 0 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 0 | 2 | 2 | 3 | 3 | 3 | 3 | 0 | 3 | 2 | 2 | 1 | 2 | 2 | 0 | 1 | 2 | 2 | 2 | 2 | 0 | 1 | 2 | 1 | 2 | 84
[9 empty] | HRS REMAINING | 83 | 82 | 81 | 80 | 79 | 79 | 79 | 79 | 78 | 77 | 75 | 74 | 72 | 72 | 69 | 69 | 67 | 66 | 64 | 63 | 61 | 60 | 60 | 58 | 56 | 55 | 53 | 52 | 51 | 50 | 49 | 48 | 46 | 45 | 43 | 43 | 41 | 39 | 36 | 33 | 30 | 27 | 27 | 24 | 22 | 20 | 19 | 17 | 15 | 15 | 14 | 12 | 10 | 8 | 6 | 6 | 5 | 3 | 2 | 0 | 2749
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Sprint 2
SPRINT 2 BACKLOG
USER STORIES / TASKS
TASK TITLE | TASK DESCRIPTION | TASK OWNER | NOTES
Account registration | As a new user, I want to register by creating a username and password so that the system can remember me and my data | Davide | Back-End
Login | As a registered user, I want to log in with my username and password so that the system can authenticate me | Davide | Back-End
View user information | As a user, I want to see my user informations, so that I can see a summary of my personal data | Stefano | Back-End
Add a travel | As a traveler, I want to create a travel, so that I can annotate all of my expanses | Stefano | Back-End
Add Expense | As a traveler, I want to annotate an expense, so that I can remember how much I spent for something | Alessandro | Back-End
Remove Expense | As a traveler, I want to remove an expense, so that I can delete a wrong expense | Alessandro | Back-End
Get all travels | As a user, I want to see all the travels I did, so that I can navigate through all the travels I did | Stefano | Back-End
End travel | As a traveler, I want to state my travel finished, so that I' not able to add expenses | Stefano | Back-End
Daily budget | As a traveler, I want to define a daily budget, so that I can monitor if I am spending too much | Alessandro | Back-End
View travel | As a traveler, I want to see a summary of the travel, so that I can see all of the info and expanses related to that travel | Alessandro | Back-End
View Day of the travel | As a traveler, I want to see a summary of my expenses in one day of traveling, so that I can see how much I spent in one day | Alessandro | Back-End
Remove Travel | As a traveler, I want to remove a travel,so that I can delete a wrong travel | Stefano | Back-End
Delete Account | As a user, I want to delete my account, so that I won't be able anymore to use the application | Davide | Back-End

## Release Backlog
SPRINT | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | STATUS KEY | WORK ESTIMATE IN HOURS
1_2 | Account registration | As a new user, I want to register by creating a username and password so that the system can remember me and my data | Davide | 4 | Completed | Not Started | 1
1_2 | Login | As a registered user, I want to log in with my username and password so that the system can authenticate me | Davide | 4 | Completed | In Progress | 2
1 | Change Password | As a user, I want to change my password, so that my account can be more secure | Davide | 4 | Completed | Completed | 4
1 | Logout | As a user, I want to logout, so that I can exit from the application | Davide | 2 | Completed |  | 8
1_2 | Delete account | As a user, I want to delete my account, so that I won't be able anymore to use the application | Davide | 4 | Completed |  | 16
1_2 | View user information | As a user, I want to see my user informations, so that I can see a summary of my personal data | Stefano | 4 | Completed |  | 18
1_2 | Add a travel | As a traveler, I want to create a travel, so that I can annotate all of my expanses | Stefano | 2 | Completed |  | 22
1_2 | Remove a travel | As a traveler, I want to remove a travel,so that I can delete a wrong travel | Stefano | 4 | Completed |  | 24
1_2 | Add Expense | As a traveler, I want to annotate an expense, so that I can remember how much I spent for something | Alessandro | 2 | Completed |  | 40
1_2 | Remove Expense | As a traveler, I want to remove an expense, so that I can delete a wrong expense | Alessandro | 4 | Completed |  | 80
3 | Travel comparison | As a traveler, I want to compare two or more travels that I did, so that I can see the difference in the expenses between them | Stefano | 4 | Completed
1_2 | Get all travels | As a user, I want to see all the travels I did, so that I can navigate through all the travels I did | Stefano | 2 | Completed
3 | Expenses comparison by categories | As a traveler, I want to compare the daily expenses, so that I can see the difference in how I spent my money in accomodations/food/ cultural places/events/transports | Alessandro | 4 | Completed
1_2 | End travel | As a traveler, I want to state my travel finished, so that I' not able to add expenses | Alessandro / Stefano | 2 | Completed
1_2 | Daily budget | As a traveler, I want to define a daily budget, so that I can monitor if I am spending too much | Alessandro | 2 | Completed
1_2 | View travel | As a traveler, I want to see a summary of the travel, so that I can see all of the info and expanses related to that travel | Alessandro | 2 | Completed
3 | Expenses comparison by days | As a traveler, I want to compare the expenses I did in two or more days of the same travel, so that I can see the difference in how much I spent in those days | Alessandro | 4 | Completed
1_2 | View Day of the travel | As a traveler, I want to see a summary of my expenses in one day of traveling, so that I can see how much I spent in one day | Alessandro | 2 | Completed
3 | Style | As a user, I want to have a good experience on the site | Davide | 4 | Completed
3 | Logger | As a system administrator, I want to check the activity of users |  | 8 | Completed

## Sprint 1
SPRINT 1 BACKLOG
USER STORIES / TASKS
TASK TITLE | TASK DESCRIPTION | TASK OWNER | NOTES
Account registration | As a new user, I want to register by creating a username and password so that the system can remember me and my data | Davide | Front-End
Login | As a registered user, I want to log in with my username and password so that the system can authenticate me | Davide | Front-End
Add a Travel | As a traveler, I want to create a travel, so that I can annotate all of my expanses | Stefano | Front-End
Add Expense | As a traveler, I want to annotate an expense, so that I can remember how much I spent for something | Alessandro | Front-End
Remove Expense | As a traveler, I want to remove an expense, so that I can delete a wrong expense | Alessandro | Front-End
Remove a travel | As a traveler, I want to remove a travel,so that I can delete a wrong travel | Stefano | Front-End
Logout | As a user, I want to logout, so that I can exit from the application | Davide | Front-End
Delete account | As a user, I want to delete my account, so that I won't be able anymore to use the application | Davide | Front-End
View user information | As a user, I want to see my user informations, so that I can see a summary of my personal data | Stefano | Front-End
Get all travels | As a user, I want to see all the travels I did, so that I can navigate through all the travel I did | Stefano | Front-End
End travel | As a traveler, I want to state my travel finished, so that I' not able to add expenses | Alessandro | Front-End
Add daily budget | As a traveler, I want to define a daily budget, so that I can monitor if I am spending too much | Alessandro | Front-End
View travel | As a traveler, I want to see a summary of the travel, so that I can see all of the info and expanses related to that travel | Alessandro | Front-End
View Day of the travel | As a traveler, I want to see a summary of my expenses in one day of traveling, so that I can see how much I spent in one day | Alessandro | Front-End

## Sprint 3
SPRINT 3 BACKLOG
USER STORIES / TASKS
TASK TITLE | TASK DESCRIPTION | TASK OWNER | NOTES
Travel comparison | As a traveler, I want to compare two or more travels that I did, so that I can see the difference in the expenses between them | Stefano | Front-End / Back-End
Expenses comparison by categories | As a traveler, I want to compare the daily expenses, so that I can see the difference in how I spent my money in accomodations/food/ cultural places/events/transports | Alessandro | Front-End
Expenses comparison by days | As a traveler, I want to compare the expenses I did in two or more days of the same travel, so that I can see the difference in how much I spent in those days | Alessandro | Front-End / Back-End
Style | As a user, I want to have a good experience on the site | Davide | Front-End
Logger | As a system administrator, I want to check the activity of users | Stefano-Davide-Alessandro | Back-End